## Sheet1
Task | Start Date | Duration (Days)
Research | 2023-10-02 | 28
Plan | 2023-10-02 | 28
Report Introduction | 2023-10-16 | 14
Develop GUI Template | 2023-10-30 | 7
Create basic web crawler | 2023-11-06 | 14
Create search functionality | 2023-11-20 | 14
Combine sections | 2023-12-04 | 7
Test | 2023-12-11 | 7
Improve web crawler | 2023-12-18 | 21
Fill out report | 2023-12-18 | 21
January Delieverable | 2024-01-08 | 4
Plan section 2 | 2024-01-15 | 14
Research AI improvements | 2024-01-15 | 14
Improve web crawler | 2024-01-29 | 14
Imrpove UI | 2024-02-12 | 7
Implement AI functionalities | 2024-02-19 | 28
Test AI functionalities | 2024-02-26 | 28
Ensure Report is up to date | 2024-03-11 | 14
Test whole program | 2024-03-25 | 7
Make improvements/fixes | 2024-04-01 | 21
Complete Report | 2024-04-15 | 28
Submission | 2024-05-13 | 1